## PTTDigital_Manday
โครงการ PTT-PSSR Online
(ระยะเวลาโครงการ ……. วัน) |  |  |  | Of2 | Of2 | Of1 |  | Of1 | Of1 | Sr1 | Of1 | Sr1 | Of1 | Sr1 | Of2 | Of2 | Of1 | Sr1
Phase | Details | Due Date Plan | Deliverables | PM | BA | SA | Developer | Developer | Tester | ABAPer | PI | FI-AR | Server | DB | DB | Infra | Security | TC
|  |  |  | ManeetipC | ManeetipC | Name | (Senior) | Name | Name | Duangjai C | WSO2 Panuwat.P | Warinee.W |  | Kornvipa.L | Wongduen.N | Thanakrit Yimyam | Name | Ariya K.
Auth & Authorization | Authentication & Authorization
| Login |  |  |  |  | 1 | 2 | 3
| Login พนักงาน ปตท. ผ่าน PTT Azure AD |  | PTT CAA, Azure AD
| Login External User ผ่าน Azure B2C |  | PTT CAA, Azure B2C
| Authentication ผ่าน PTT CAA |  | PTT CAA
| Authorization | [5 empty] | 3 | 3
CRUD กลุ่มผู้ใช้งาน / กำหนดสิทธิ์ตามเมนู
| กำหนดผู้อนุมัติตามประเภทงาน / พื้นที่ |  | PTT PIS
แบบฟอร์ม PSSR Check List | แบบฟอร์ม PSSR Check List
| ส่วนที่ 1 ข้อมูลของงาน (Requester) |  |  |  |  | 3 | 3
| เลือกลักษณะของงาน 3 ประเภท 1. Major Turnaround 2. โครงการก่อสร้าง 3. งานอื่นๆ | [6 empty] | 3
| เลือกพื้นที่โรงแยกก๊าซ (เลือกได้ 1 พื้นที่) | [6 empty] | 1
| ส่งขออนุมัติผู้ทบทวนเอกสาร | [6 empty] | 1
| เพิ่ม PSSR Leader (ระดับหัวหน้าหน่วยควบคุมผลิตขึ้นไป) |  | PTT PIS |  |  |  |  | 2
| เพิ่ม PSSR Member (อายุงาน 3 ปีขึ้นไป หรือได้รับอนุมัติ) |  | PTT PIS |  |  |  |  | 1.5
| ส่วนที่ 2 Before start up (ยอมรับไม่ได้) |  |  |  |  | 3 | 3
| Requester: สร้างรายการที่ต้องดำเนินการ (เพิ่มได้ > 1 รายการ) | [6 empty] | 3
| Requester: ระบุรายละเอียด / วันกำหนดแล้วเสร็จ / ผู้รับผิดชอบ (ค้นหาจากรหัสพนักงาน) |  | PTT PIS |  |  |  |  | 2
| Requester: เลือกผู้อนุมัติตามประเภทงาน / พื้นที่ | [6 empty] | 1.5
| Requester: กำหนดผู้อนุมัติสำรอง (กรณีผู้อนุมัติหลักไม่สะดวก) | [6 empty] | 0.5
| การแจ้งเตือนผู้รับผิดชอบ Before start up (ล่วงหน้า 7, 3 วัน และวันกำหนด) job | [6 empty] | 3
| การแจ้งเตือนเมื่อเกินกำหนด (ทุก 3 วัน, CC: Leader, Requester) job | [6 empty] | 3
| PSSR Team: ดูรายละเอียดงาน / อัพเดท Status และรายละเอียด | [6 empty] | 1
| PSSR Team: แนบไฟล์ภาพประกอบ เพื่อปิดงาน | [6 empty] | 1
| การแจ้งเตือน PSSR Team (แจ้งเมื่ออัพเดทแต่ละรายการ / เมื่องานครบทุกรายการ) job | [6 empty] | 3
| ส่งขออนุมัติ Before start up (เมื่อผู้รับผิดชอบดำเนินการครบทุกรายการ) | [6 empty] | 1
| ส่วนที่ 3 After start up (ยอมรับได้) |  |  |  |  | 2 | 3
| Requester: สร้างรายการ After start up (ระบุรายละเอียด / วันที่ / ผู้รับผิดชอบ) |  | PTT PIS |  |  |  |  | 2
| การแจ้งเตือนผู้รับผิดชอบ After start up (ล่วงหน้า 7, 3 วัน และวันกำหนด) job | [6 empty] | 3
| PSSR Team: อัพเดท Status (After start up) | [6 empty] | 1
| การแจ้งเตือน PSSR Team After start up (แจ้งเมื่ออัพเดท / เมื่องานครบทุกรายการ) job | [6 empty] | 3
| ส่งขออนุมัติ After start up (เมื่อครบทุกรายการ) | [6 empty] | 1
| ปิดงาน / Sign off (Requester Review และกรอกรายละเอียด) | [6 empty] | 2
| ส่ง Email แจ้งผู้เกี่ยวข้องเมื่อ Sign off (ชื่องาน, พื้นที่, Before/After count, วันแล้วเสร็จ, Link) job | [6 empty] | 3
| ฟังก์ชันร่วม (Requester & PSSR Team) |  |  |  |  | 1 | 1
| Print แบบฟอร์ม PSSR Check List (ข้อมูลงาน, Before start up, After start up) | [6 empty] | 2
| Print รายชื่อ PSSR Team เพื่อลงนาม | [6 empty] | 1
| History Log ของรายการ | [6 empty] | 1
เมนู Admin | เมนู Admin |  |  |  |  | 2 | 3
| บริหารจัดการกลุ่มผู้ใช้งาน (เพิ่ม / ลด สิทธิ์) | [6 empty] | 2
| บริหารจัดการผู้ใช้งาน |  | PTT PIS |  |  |  |  | 2
| บริหารจัดการสิทธิ์ตามเมนู | [6 empty] | 2
| บริหารจัดการลักษณะของงาน (Job Type) | [6 empty] | 2
| บริหารจัดการพื้นที่การทำงาน | [6 empty] | 2
| บริหารจัดการการตั้งค่าแจ้งเตือน | [6 empty] | 2
| เมนูตรวจสอบการส่งอีเมลจากระบบ | [6 empty] | 2
| บริหารจัดการข้อมูลบนแบบฟอร์ม | [6 empty] | 2
การจัดเก็บ ข้อมูล | การจัดเก็บข้อมูล |  |  |  |  | 1 | 1
จัดเก็บข้อมูลย้อนหลัง 5 ปี
| Archive ข้อมูลที่มีอายุมากกว่า 5 ปี (ปีละ 1 ครั้ง สิ้นปี) job | [6 empty] | 3
Dashboard | Dashboard |  |  |  |  | 3
| Advance Search (ค้นหาตามปี / พื้นที่ / ลักษณะงาน / ชื่อ) | [6 empty] | 3
| Export ข้อมูลรายการที่เลือก | [6 empty] | 3
| Chart: สรุป PSSR ตามพื้นที่โรงแยกก๊าซ (จำนวน PSSR ปีปัจจุบัน แยกตามพื้นที่) | [6 empty] | 2.5
| Chart: สรุป PSSR ตามลักษณะงาน (Major Turnaround / โครงการก่อสร้าง / อื่นๆ) | [6 empty] | 2
| KPI: รายการที่ยังต้องแก้ไข ณ วันนี้ (Outstanding Before/After start up items) | [6 empty] | 2
Coverity | Coverity API | [6 empty] | 6
| Coverity FrontEnd | [6 empty] | 1
| ★ รวมทั้งหมด (MD) |  |  |  |  | 16 | 19 | 91 | 0
[6 empty] | 8500 | 14000 | 8500
[6 empty] | 136000 | 266000 | 773500
1175500

## PSM-Platform (API)
Coverity Security Report — PSM-Platform (API) — Snapshot 21761
Snapshot ID | 21761
Analysis Date | Jun 23, 2026
Lines of Code | 20,451
Security Score | 50 / 90 (Target) ❌ Fail
OWASP Top 10 Issues | 26 (Target: 0) ❌
CWE/SANS Top 25 | 42 (Target: 0) ❌
Issues By Severity
Severity | Count | % of Total
Very High | 88 | 82.2%
High | 19 | 17.8%
Medium | 0 | 0.0%
Low | 0 | 0.0%
Very Low | 0 | 0.0%
Informational | 0 | 0.0%
Total | 107 | 100%
CWE | CWE Name | Severity | Issues | Issue Type / Description | Avg Min per Issue | Manday (8h) | Technical Impact
CWE-22 | Path Traversal | Very High | 12 | Filesystem path / URI manipulation — use whitelist input validation | 30 | 0.75 | Execute unauthorized code
CWE-915 | Mass Assignment | Very High | 46 | Improperly Controlled Object Attributes — use DTO / whitelist allowed fields | 20 | 1.9167 | Execute unauthorized code
CWE-918 | Server-Side Request Forgery (SSRF) | Very High | 7 | URL manipulation — validate and restrict outbound requests | 30 | 0.4375 | Execute unauthorized code
CWE-260 | Password in Configuration File | Very High | 2 | Hardcoded credentials in source code — use secure vault / env vars | 20 | 0.083333 | Gain privileges
CWE-330 | Use of Insufficiently Random Values | Very High | 1 | Cryptographically weak PRNG — use CryptGenRandom / hw_rand() | 30 | 0.0625 | Gain privileges
CWE-352 | Cross-Site Request Forgery (CSRF) | Very High | 17 | Missing anti-CSRF token on state-changing endpoints | 25 | 0.88542 | Gain privileges
CWE-749 | Exposed Dangerous Method or Function | Very High | 1 | HTTP allowed-methods not restricted (e.g. DELETE/PUT exposed) | 20 | 0.041667 | Gain privileges
CWE-759 | One-Way Hash without a Salt | Very High | 1 | Password hashed without salt — use bcrypt/argon2 | 20 | 0.041667 | Gain privileges
CWE-89 | SQL Injection | High | 9 | Non-constant SQL / string-concatenated query — use parameterized queries | 45 | 0.84375 | Bypass protection mechanism
CWE-338 | Weak Pseudo-Random Number Generator | High | 1 | Insecure PRNG in crypto context — use cryptographic RNG | 30 | 0.0625 | Bypass protection mechanism
CWE-760 | One-Way Hash with Predictable Salt | High | 2 | Password hashed with predictable salt — use random salt per-password | 20 | 0.083333 | Bypass protection mechanism
CWE-561 | Dead Code | High | 5 | Constant variable guards unreachable code — remove dead code | 15 | 0.15625 | Denial of service, unreliable execution
CWE-99 | Resource Injection | High | 2 | URL/Resource identifier injection — validate resource identifiers | 30 | 0.125 | Modify data
Total |  |  | 106 |  |  | 5.4896

## PSM-Platform (Frontend)
Coverity Security Report — PSM-Platform-Frontend — Snapshot 21769
Snapshot ID | 21769
Analysis Date | Jun 23, 2026
Lines of Code | 51,643
Security Score | 58 / 90 (Target) ❌ Fail
OWASP Top 10 Issues | 3 (Target: 0) ❌
CWE/SANS Top 25 | 7 (Target: 0) ❌
Issues By Severity
Severity | Count | % of Total
Very High | 7 | 58.3%
High | 5 | 41.7%
Medium | 0 | 0.0%
Low | 0 | 0.0%
Very Low | 0 | 0.0%
Informational | 0 | 0.0%
Total | 12 | 100%
CWE | CWE Name | Severity | Issues | Issue Type / Description | Avg Min per Issue | Manday (8h) | Technical Impact
CWE-476 | NULL Pointer Dereference | Very High | 4 | Bad use of null-like value — add null checks before dereference | 20 | 0.16667 | Execute unauthorized code
CWE-79 | Cross-Site Scripting (XSS) | Very High | 3 | DOM-based XSS — sanitize user-controlled input before DOM insertion | 30 | 0.1875 | Execute unauthorized code
CWE-688 | Function Call With Incorrect Variable | High | 1 | Typo in identifier / wrong argument type — code review & type checking | 15 | 0.03125 | Denial of service, unreliable execution
CWE-922 | Insecure Storage of Sensitive Information | High | 4 | Sensitive data written to localStorage — use sessionStorage or server session | 20 | 0.16667 | Modify data
Total |  |  | 12 |  |  | 0.55208